## MOM
MINUTES OF MEETING CASAGRAND TUDOR PROJECT
| CG team : Mr.Mangal,Mr.Rajiv,Mr.Ramesh, Arun Sliambarasan, Mr.Raja,Mr.Moorthy,Mr.Krishna Prabhu | Tudor Owners |  | Date : 1 Feb 2025
SITE : Tudor |  | Location : F block Stilt floor
SL.NO | DISCUSSION POINTS | ACTION PLAN | STATUS
1 | Project status update | Project status is enclosed with mail | Open
2 | WTP iron remover & softener status, additional bore well -Owners demanded WTP flow diagram with the details of sumps and CG agreed to provide the same -When owners raised a query on sufficiency of existing 250 KLD considering the summertime, Mr. Rajeev informed that with the present bore wells they can extract 27,000 Liters /hr. which comes to 324 KLD (12Hours operation) which is more than the required 250 KLD. -Owners clarified that the present 6 Bore wells yield is only 100KLD as per the Bore well report which is considering 50% yield and additional bore wells to be provided to compensate the balance 150KLD. | Iron removal & UF filter will install at March 31st 2025,Will check the feasibility of additional bore well. Out of 10 bore wells dug 6 bore wells have water with less TDS and these 6 bore wells with Iron removal, water softener will be connected and will be ready by March’25 end. After run, RO option will be decided based on owner’s consent. Request of additional bore well from owners’ side will be considered and will be done before 15th Feb 2025 Decision on request of 3 wells from owner’s side will be decided after discussion with the management as CG has not done any wells in any of their projects and it’s not in their scope and they will inform owners on this before 15th Feb 2025. | Open | Iron removal &UF filter work completed on 31-03-2025. we have provide 3 well the project team and well vendor checking work on process.
3 | Metro water status. Provision of separate sump for metro water When owners raised query on a separate sump for Metro water CG informed, they will provide transfer sump of 5000 Liters capacity transfer sump, which will be automated to transfer the water to the raw water sump, which is considered as main sump. CG also clarified that this has been followed successfully in their other projects. But the owners insisted to provide a min capacity of 15,000 liters. | Metro transfer sump will be provided & metro connection is under decision CG informed Metro water pipeline is available up to Brigade and once after EB work is completed, they will proceed with Metro water connection and OSR one by one due to local body issues. | Open
4 | STP status | Once 60% customer occupied will start the operation | Open
5 | Solid waste management | Once IFMS Team Will explain the process of garbage segration the community | Open
6 | EB Status CG informed there are 3 transformers as provided below: • Yard 1 – Covering Block A, B &H kept near B block with 250 KVA capacity • Yard 2 – Covering C, D & E block kept opposite to D block with 500 KVA capacity • Yard 3 – Covering J, F, &G block kept near F block with 250 KVA capacity Owners raised queries whether yard 2 transformer in which common amenities are connected can withstand the load and raised question whether common amenities will be charged at commercial rates. The total power requirement as per CG provided document is 3675 KW and as per EIA it is 4057KVA and owners insisted that this must be arranged with EB | EB work is under progress, 2-nos transformer erected,143 meters fixed A,B & J block, Once transformer charged will provide Eb supply for meter fixed blocks other block gets DG supply once received balance EB meters will change to EB for other blocks. CG clarified all transformers are looped and total capacity need to be considered and confirmed all the rates will fall under domestic tariff. The transformers capacity is governed by EB only and CG has no control on it. EB will either add more transformers or upgrade the existing ones based on the consumption demand. All EB work will be completed by the end of Feb’25. EB supply will be given once the meter is connected to the blocks. | Open
7 | Solar is built with approx. 1/4th of the open area and not 1/3rd, with a capacity of 70KW. Owners raised question why only 1/4th area is given solar panel while as per CMDA its mentioned as 1/3rd., CG mentioned approval as per CMDA its 1/3 rd and as per TNEB its 1/4th. They are awaiting confirmation as to which one they need follow. Owners insisted CG to go ahead with CMDA approval and requested to share terrace area calculation | Solar provided as per norms it is on grid only | Open
8 | Podium area grill is in loose condition | Agreed will check & it will get rectify | Open | we will be completed on 28.02.2025.
9 | B,D,E,F,G,H Pathway are very narrow, The car parking in front of the lobby not to be allocated to anyone, which will facilitate a free pathway | Will check the condition & update | Open | 31-03-2025
10 | DOG Menace | Once IFMS starts will reduce the dog menace | Open
11 | Car parking Allocation | Once car park marking finished at March 31st 2025 will circulate the allocation mail to all owners through CRM | Open
12 | Clubhouse Launch | Once QC clearance done will circulate mail to all owners through Icare | Open | 31-03-2025
13 | IFMS Take over after WTP completion | Once Our review completed will circulate mail to all owners through Icare (IFMS start date to end date) | Open | 31-03-2025
14 | OSR & Back entrance status OSR approval will be obtained after the completion of EB connection. CG clarified that this is due to the issues with the local bodies and being tackled one by one. After OSR completion free maintenance for OSR will have a separate 6-month free maintenance. Query raised by owners on the maintenance charges to the owners if OSR is having a separate 6month free maintenance. CG confirmed that the difference in the period will be considered, and the maintenance charges will be calculated accordingly. | Internal discussion, We will update | Open
15 | Requested Boom barrier for both gates (Main & Rear Gate) | Will update the status of Boom barrier once discussion done with internal team | Open
16 | Need additional Internet provider | Will check with team | Open | This is month Feb-25 .4th weeks net work inspection the site.
17 | Visitor Car parking (41 no's) & clubhouse parking (15 no's) | Once the car parking marking completed in the site we can able to conform the status parking | Open
18 | EV Charger point additionally 2 points needed | As per GFC we done EV charging point | Open | 15-03-2025
19 | New Lift need to be change in B block | We will not change new lift will repair lift & required will replace the parts will refurbished | Open | we will discuses then sent to mail.
20 | Building elevation light should provide all blocks | As per GFC we done the elevation light , | Open | we will discuses then sent to mail.
21 | Lumber room should be handed over to Association | Need Conformation from all the 8 owners regarding Lumber room handover .Once we receive will conformation will update the status | Open
22 | C block lift when will operate | Lift will operate at Feb-10th-2025 | Completed | 19-02-2025
23 | Pattas when will update | Owners need to visit the nearest E-Serve and fill the form and submit | Open
24 | Lift to Security intercom facility | Will provide intercom facility at 10-02-2025 | Open | we will discuses then sent to mail.
25 | Fire Extinguisher is expired | As we checked its not expired, if any caught will refill | Open
27 | Tower booster need to be provided in all terrace in Airtel & Join brand | Once the association will discuss the core team for tower booster in te site ,Meanwhile will check the team tocheck the network range in the community | Open | This is month Feb-25 .4th weeks net work inspection the site.
28 | EB Name Transfer | We schedule the service Camp for EB name transfer | Open